## Project Plan
PROJECT X - AUTOMATED ATTENDANCE SYSTEM
Deadline: |  |  | 2025-05-02 |  | Days Left: 36 Days |  |  |  |  | Task Done: 7/32
Plan Start Date - March 1, 2025 |  |  | Plan End Date - May 13, 2025 | Actual Start Date - March 21, 2025 |  |  | Actual End Date - May 2, 2025
Task ID | Task Name | Sub Task ID | Sub Task Name | Deliverables | Assignee | Estimated Hours (Days) | Plan Start Date | Actual Start Date | Plan End Date | Actual End Date | Status
1 | Project Initiation | 1.1 | Define project objectives | Project scope document | Wenona Marie M. Montemayor | 1 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | Done
|  | 1.2 | Identify stakeholders | Stakeholder list | Neil Roy G. Omongos | 1 | 2025-03-22 | 2025-03-22 | 2025-03-22 | 2025-03-22 | Done
|  | 1.3 | Conduct feasibility study | Feasibility report | Shamaiah Lee Cadut | 1 | 2025-03-23 | 2025-03-23 | 2025-03-23 | 2025-03-23 | Done
|  | 1.4 | Create project plan | Project plan document | Wenona Marie M. Montemayor | 1 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | Done
|  | 1.5 | Obtain approvals | Approved project charter | Neil Roy G. Omongos | 1 | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | Done
2 | Requirement Analysis | 2.1 | Gather functional requirements | Requirement specification document | Hello World! | 1 | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2025-03-26 | Done
|  | 2.2 | Gather non-functional requirements | Performance & security requirements | Shamaiah Lee Cadut | 1 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | Done
|  | 2.3 | Define system architecture | System architecture diagram |  | 2 | 2025-03-28 |  | 2025-03-28 |  | Pending
|  | 2.4 | Create wireframes/mockups | UI wireframes |  | 2 | 2025-03-30 |  | 2025-03-30 |  | Pending
3 | Design Phase | 3.1 | Database design | ERD and database schema |  | 3 | 2025-04-01 |  | 2025-04-01 |  | Pending
|  | 3.2 | API design | API documentation |  | 2 | 2025-04-04 |  | 2025-04-04 |  | Pending
|  | 3.3 | UI/UX design | Final UI/UX designs |  | 2 | 2025-04-06 |  | 2025-04-06 |  | Pending
|  | 3.4 | Security design | Security measures document |  | 4 | 2025-04-08 |  | 2025-04-08 |  | Pending
4 | Development Phase | 4.1 | Set up development environment | Configured development tools |  | 1 | 2025-04-12 |  | 2025-04-12 |  | Pending
|  | 4.2 | Frontend development (React Native) | Initial UI screens |  | 3 | 2025-04-13 |  | 2025-04-13 |  | Pending
|  | 4.3 | Backend development | Working backend APIs |  | 5 | 2025-04-16 |  | 2025-04-16 |  | Pending
|  | 4.4 | QR Code scanning implementation | Functional QR scanner module |  | 2 | 2025-04-21 |  | 2025-04-21 |  | Pending
|  | 4.5 | GPS validation implementation | Functional GPS validation |  | 3 | 2025-04-23 |  | 2025-04-23 |  | Pending
|  | 4.6 | Secure storage implementation | Encrypted storage module |  | 2 | 2025-04-26 |  | 2025-04-26 |  | Pending
|  | 4.7 | Testing unit integration | Test reports |  | 1 | 2025-04-28 |  | 2025-04-28 |  | Pending
5 | Testing & QA | 5.1 | Functional testing | Test case reports |  | 1 | 2025-04-29 |  | 2025-04-29 |  | Pending
|  | 5.2 | Security testing | Security vulnerability report |  | 1 | 2025-04-30 |  | 2025-04-30 |  | Pending
|  | 5.3 | User acceptance testing | User feedback & approval |  | 1 | 2025-05-01 |  | 2025-05-01 |  | Pending
6 | Deployment | 6.1 | Prepare deployment environment | Deployment guide |  | 1 | 2025-05-02 |  | 2025-05-02 |  | Pending
|  | 6.2 | Deploy backend API | Hosted backend |  | 2 | 2025-05-03 |  | 2025-05-03 |  | Pending
|  | 6.3 | Deploy mobile app (beta) | Beta version released |  | 1 | 2025-05-05 |  | 2025-05-05 |  | Pending
|  | 6.4 | Fix deployment issues | Issue resolution report |  | 3 | 2025-05-06 |  | 2025-05-06 |  | Pending
|  | 6.5 | Release final version | Live mobile app |  | 1 | 2025-05-09 |  | 2025-05-09 |  | Pending
7 | Final Demonstration | 7.1 | Prepare presentation materials | Presentation slides |  | 1 | 2025-05-10 |  | 2025-05-10 |  | Pending
|  | 7.2 | Conduct demo for stakeholders | Live demonstration |  | 1 | 2025-05-11 |  | 2025-05-11 |  | Pending
|  | 7.3 | Gather final feedback | Feedback report |  | 1 | 2025-05-12 |  | 2025-05-12 |  | Pending
|  | 7.4 | Project closure & documentation | Final project report |  | 1 | 2025-05-13 |  | 2025-05-13 |  | Pending
Formulas:
Actual End Date - May 2, 2025 = [Actual End Date - May 2, 2025, row above]+[Estimated Hours (Days), row above]
Actual Start Date = [Actual Start Date, row above]+[Estimated Hours (Days), row above]
Plan End Date = [Plan End Date, row above]+[Estimated Hours (Days), row above]